MINUTES OF THE COLLIER COUNTY PARKS AND RECREATION ADVISORY BOARD MEETING
Naples, Florida — October 15, 2025

LET IT BE REMEMBERED, the Collier County Parks and Recreation Advisory Board, in and for the County of Collier, having conducted business herein, met on this date at 2:00 P.M. in REGULAR SESSION at 15000 Old Livingston Rd, Naples, FL 34109, USA, with the following members present:

Chairman: Edward “Ski” Olesky

Vice Chairman: Josh Fruth

Rebecca Gibson-Laemel

Eric Kelly

ALSO PRESENT:

James Hanrahan – Director

Said Gomez – Regional Manager

Brian Maloney – Director, Facilities

Eric Short – Superintendent, Maintenance

Any persons needing the verbatim record of the meeting may request a copy of the audio recording from the Collier County Parks and Recreation Department.

### 1.	Call to Order

PRESIDING Chairman Edward “Ski” Olesky called the meeting to order at 6:00 p.m.

The Pledge of Allegiance and invocation were conducted.

# .

### 2.	Agenda review:

No motion or vote recorded.

### 3.	Approval of the meeting

No motion or vote recorded.

### 4. 	New Business

No new business discussed.

### 5. 	Old Business

A. Immokalee Sports Complex Update – Presentation by Brian Maloney

Mr. Brian Maloney, Director of Facilities, provided an update on the Immokalee Sports Complex project.

Highlights included:

Project divided into three phases: Phase 1A (open turf fields and lighting), Phase 1B (restroom and storage), Phase 2 (aquatics center). Design 100% complete; permitting ongoing with variance petition for landscaping reduction to accommodate full-size fields. Approvals: construction phasing plan, Immokalee Water and Sewer District, South Florida Water Management District Water Use Permit and ERP. Procurement timeframe: eight months; construction: nine months; fields projected completion 2027. Stormwater management: perforated piping and gravel underlayment, exfiltration trenches, new outlet structure. Construction start projected September 2026; fields maintained until then, with alternatives (e.g., Big Corkscrew, CRA sites) to be coordinated with YSFA presidents.

Discussion:

Discrepancy noted on 2027 timeline, with staff confirming it was presented since April 2024. Concerns raised about soccer season closure (December 2025–2026), stormwater flooding, and community communication. Staff committed to monthly updates, working with organizations on alternatives, and addressing flooding with current drainage plans.

No action required; informational presentation.

### 6.	Board / Public Comments

- Public comments were received as follows:

- Maria Sierra raised questions about the projected timeline (disputed 2027 completion), fields closure during soccer season, alternative plans, and stormwater management.

- Tom expressed concern about construction timing conflicting with soccer season, lack of a plan during closure, and requested a pre-construction meeting.

- Randy Geron discussed summer field closures, impacts on youth programs, fairness with other parks, and lighting issues.

- Ms. Marcy inquired about budget ($4.2 million set aside, potential $3 million additional), procurement, and economic factors.

- Mr. Mangrove questioned delays from prior projections, procurement process, and contractor outreach.

- Additional speakers thanked staff, requested online updates, and highlighted transportation concerns for relocated programs.

7. 	Manager Updates

No additional staff reports presented.

8. 	Director’s Report

Board expressed frustration with project delays and turnover, emphasizing the need for accountability and seeing the project through.

9. 	Adjournment

# Motion: To adjourn.

Meeting adjourned at 6:58 p.m.

COLLIER COUNTY

PARKS AND RECREATION ADVISORY BOARD

Edward “Ski” Olesky, Chairman

These minutes were approved by the Board/Chairman on 	, as presented (choose one) 	, or as amended 	.